## Worksheet
Task ID | Task Description | Responsible Party | Due Date | Status | Compliance Requirement | Notes
T001 | Conduct initial compliance review | Compliance Team | 2024-04-15 | Not Started | ISO 9001 Clause 4.3
T002 | Develop policy documentation | Policy Manager | 2024-04-20 | In Progress | ISO 9001 Clause 7.5
T003 | Train staff on compliance procedures | HR Department | 2024-04-25 | Not Started | ISO 9001 Clause 7.2
T004 | Audit internal processes | Internal Auditor | 2024-05-01 | Not Started | ISO 9001 Clause 9.2
T005 | Prepare for external certification audit | Compliance Manager | 2024-05-10 | Not Started | ISO 9001 Clause 9.4
T006 | Submit documentation to certifying body | Compliance Team | 2024-05-15 | Not Started | ISO 9001 Clause 9.3
Total Tasks: | [5 empty] | 6