## Worksheet
Compliance Tracking - Project Plan
Task ID | Task Description | Responsible Party | Start Date | Due Date | Status | Compliance Standard
TASK001 | Conduct Risk Assessment | Jane Smith (Risk Dept) | 2024-05-01 | 2024-05-15 | In Progress | CSSA 2.3.1
TASK002 | Update Security Policies | Mike Johnson (Security) | 2024-05-05 | 2024-05-25 | To Do | GRC 4.7.9
TASK003 | Employee Compliance Training | Sarah Lee (HR) | 2024-05-10 | 2024-06-15 | In Progress
TASK004 | Third-party Audit Preparation | Luis Rodriguez (Audit) | 2024-05-18 | 2024-06-30 | Not Started
TASK005 | Firmware Compliance Check | Alex Kim (IT Ops)
Total Tasks: | 5