## Worksheet
Compliance Tracking - Project Plan (Client View)
Project ID: PRJ-2024-001 ¦ Period: Q3 2024 ¦ Prepared For: Client XYZ
Task ID | Task Description | Responsible Party | Scheduled Start Date | Scheduled End Date | Status (Compliance)
TASK-001 | Conduct Security Audit & Risk Assessment | Internal IT Team | 2024-07-15 | 2024-07-31 | Compliant
TASK-002 | Update Data Encryption Protocols | Security Compliance Officer | 2024-07-18 | 2024-08-15 | Pending Review
TASK-003 | Employee Training on GDPR Guidelines | HR Department | 2024-07-25 | 2024-08-10 | Compliant
TASK-004 | Third-party Vendor Risk Assessment | Procurement Team | 2024-07-30 | 2024-08-25 | Non-compliant (Pending)
TASK-005 | Implement Incident Response Plan Testing | Cybersecurity Team | 2024-08-12 | 2024-08-31 | Pending Approval
TASK-006 | Document Retention Policy Review | Legal Department | 2024-08-15 | 2024-09-15 | In Progress