## Worksheet
Compliance Tracking - Project Plan
Task ID | Task Description | Responsible Party | Due Date | Status | Compliance Requirement | Notes/Comments (Editable)Click to edit
CT-001 | Conduct initial risk assessment | John Doe | 2023-10-15 | Not Started | ISO 27001 Clause 6.1 | Initial review scheduled for week 4.
CT-002 | Develop compliance policy document | Jane Smith | 2023-11-01 | In Progress | GDPR Article 30 | Draft completed, awaiting legal review.
CT-003 | Train staff on data protection policies | Mike Johnson | 2023-11-15 | Pending | ISO 27001 Clause 7.2 | Schedule training sessions with HR.
CT-004 | Audit internal systems for compliance | Sarah Lee | 2023-12-01 | Not Started | NIST SP 800-53 Rev. 4 | System access logs to be reviewed.
CT-005 | Submit compliance report to management | Alex Brown | 2023-12-15 | Not Started | Internal Audit Policy 4.3 | Finalize findings from audits.