## Worksheet
Compliance Tracking Project Plan (Extended Version)
Project ID | Project Name | Compliance Area | Regulation/Standard | Milestone | Description | Status | Responsible Team/Person | Due Date | Actual Completion Date | Audit Result (Pass/Fail) | Notes/Comments
P001 | Data Privacy Implementation | Data Protection | GDPR, CCPA | Phase 1 - Assessment & Mapping | Conduct data inventory and classification across all systems. | In Progress | Privacy Team - J. Smith | 2023-10-31 | - | - | Initial review completed; data sources under verification.
P001 | Data Privacy Implementation | Data Protection | GDPR, CCPA | Phase 2 - Policy Development | Create updated data processing policies and consent mechanisms. | In Progress | Legal & Compliance - A. Lee | 2023-11-15 | - | - | First draft under review with legal counsel.
P001 | Data Privacy Implementation | Data Protection | GDPR, CCPA | Phase 3 - System Updates & Training | Implement privacy controls in CRM and train staff. | In Progress | Tech Team - M. Brown | 2023-12-10 | - | - | Integration testing in progress; training modules ready.
Security Compliance - IT Infrastructure Audit (Q4)
P002 | Network Security Enhancement | IT Security | ISO 27001, NIST SP 800-53 | Firewall Configuration Review | Validate firewall rules and update outdated policies. | Compliant | Security Ops - T. Nguyen | 2023-10-15 | 2023-10-14 | Pass | All rules documented and validated via automated tooling.
P002 | Network Security Enhancement | IT Security | ISO 27001, NIST SP 800-53 | Endpoint Protection Update | Deploy updated antivirus and EDR solutions on all endpoints. | In Progress | IT Operations - L. Patel | 2023-11-05 | - | - | 68% deployed; rollout scheduled completion by Nov 3.
HR & Employment Compliance (Ongoing)
P003 | Employee Onboarding Process | Employment Law | Federal Labor Standards, ADA, EEOC Guidelines | Update Onboarding Checklist & Training Modules | Revise onboarding documentation to include compliance training. | Compliant | HR - S. Johnson | 2023-09-30 | 2023-10-01 | Pass | New modules integrated into HRIS system.
P003 | Employee Onboarding Process | Employment Law | Federal Labor Standards, ADA, EEOC Guidelines | Manager Training Sessions (Quarterly) | Conduct mandatory manager training on anti-harassment and equity. | Compliant | HR - S. Johnson | 2023-11-10 | 2023-11-08 | Pass | All managers completed training; records updated.
Financial & Tax Compliance (Annual)
P004 | Fiscal Year 2023 Audit Preparation | Financial Reporting | GAAP, SOX Section 404 | Internal Control Testing | Verify accuracy and completeness of financial controls. | In Progress | Audit & Finance - K. Williams | 2023-11-30 | - | - | Testing phase underway; 75% of controls reviewed.
Overall Project Status Summary
Total Tasks |  |  |  | 12 | Compliant: |  |  |  |  | 6 (50%)
In Progress |  |  |  | 5 | In Progress: |  |  |  |  | 5 (42%)
Not Started |  |  |  | 1 | Pending: |  |  |  |  | 1 (8%)