## Worksheet
Compliance Tracking - Project Plan - Financial View
Project ID: PROJ-2024-COMPL-001 ¦ Status: Active ¦ Reporting Period: Q2 2024
Task ID | Task Description | Responsible Team | Start Date | End Date | Budget Allocated ($) | Budget Spent ($) | Status | Compliance Level
COMPL-001 | Regulatory Audit Preparation | Compliance Department | 2024-04-01 | 2024-05-15 | 18,500.00 | 9,356.78 | In Progress | High (92%)
COMPL-002 | Data Privacy Assessment (GDPR/CCPA) | IT & Legal | 2024-04-15 | 2024-06-30 | 35,750.00 | 17,891.45 | In Progress | High (87%)
COMPL-003 | Security Certification Renewal (SOC 2) | Security Team | 2024-05-10 | 2024-07-31 | 45,600.00 | 8,943.12 | Not Started | Moderate (75%)
COMPL-004 | Internal Policy Review & Update | HR & Legal | 2024-06-01 | 2024-07-15 | 15,300.00 | 3,987.65 | Not Started | High (89%)
COMPL-005 | Cross-Departmental Training Sessions | Training & Compliance | 2024-07-15 | 2024-09-30 | 12,850.00 | 1,367.89 | Not Started | Moderate (78%)
Total: |  |  |  |  | 127,000.00 | 41,546.89