## Worksheet
Compliance Tracking - Project Plan (Manager View)
Task ID | Task Description | Responsible Team | Compliance Standard | Due Date | Status (Compliance) | % Complete | Risk Level
PROJ-001 | Finalize project scope document | Project Management Office | ISO 9001:2015 - QMS Requirements | 2023-12-31 | Compliant | 100% | Low
PROJ-002 | Conduct internal audit for Phase 1 deliverables | Audit & Compliance Team | ISO 14001:2015 - Environmental Management | 2023-12-25 | Compliant | 95% | Medium
PROJ-003 | Update cybersecurity protocols per NIST SP 800-53 | SysAdmin & Security Team | NIST SP 800-53 Rev.4 - Security Controls | 2024-01-15 | Non-compliant (Pending Review) | 78% | High
PROJ-004 | Employee training on GDPR compliance updates | HR & Legal Department | GDPR Article 32 - Data Protection Measures | 2024-01-31 | Conditional (Training in progress) | 65% | Medium
PROJ-005 | Validate third-party vendor compliance documentation | Risk Management Unit | SOC 2 Type II - Security & Availability Criteria | 2024-01-10 | Compliant (On track) | 85% | Low
PROJ-006 | Document and archive all project records per retention policy | Data Governance Team | ISO 15489:2016 - Records Management | 2024-03-31 | Compliant (Initiated) | 50% | Low
Summary Metrics
Total Tasks:6
Compliant:3 (50%)
Pending/Conditional:2 (33%)
Non-compliant:1 (17%)
Critical Risk Alert: One task at High Risk — Immediate attention required.