## Worksheet
Task ID | Task Description | Responsible Party | Start Date | End Date | Status | Compliance Requirement
TASK-001 | Review Regulatory Standards | Jane Doe | 2023-10-01 | 2023-10-05 | In Progress | ISO 9001:2015 Clause 4.3
TASK-002 | Document Risk Assessment | John Smith | 2023-10-06 | 2023-10-15 | To Do | OHSAS 18001 Requirement 6.1.2
TASK-003 | Conduct Internal Audit | Alice Johnson | 2023-10-16 | 2023-10-25 | To Do | ISO 14001:2015 Clause 9.2
TASK-004 | Update Compliance Documentation | Robert Brown | 2023-10-26 | 2023-11-05 | To Do | NIST SP 800-53 Rev. 4 Control IA-2
TASK-005 | Training Completion - Compliance Awareness | Sarah Lee | 2023-11-06 | 2023-11-15 | To Do | EPA 40 CFR Part 75.8a Requirements