## Worksheet
Task ID | Task Description | Responsible Party | Start Date | End Date | Status | Compliance Requirement ID(Reference) | Milestone?(Yes/No)
T001 | Conduct Initial Compliance Assessment | Compliance Team | 2024-01-15 | 2024-01-31 | In Progress | CMP-RQ-001(ISO 9001) | Yes
T002 | Develop Compliance Training Program | HR & Compliance Dept. | 2024-02-01 | 2024-02-15 | To Do | CMP-RQ-003(GDPR) | No
T003 | Review Policy Documents for Regulatory Alignment | Legal & Compliance Team | 2024-02-16 | 2024-03-15 | To Do | CMP-RQ-007(SOX) | Yes
T004 | Execute Internal Audit for Compliance Readiness | Audit Committee | 2024-03-16 | 2024-04-15 | To Do | CMP-RQ-011(HIPAA) | Yes
T005 | Submit Compliance Report to Governance Board | Compliance Officer | 2024-04-16 | 2024-04-30 | To Do | CMP-RQ-015(Oversight) | Yes