## Worksheet
Compliance Tracking - Project Plan
Task ID | Task Description | Responsible Party | Compliance Requirements |  |  | Due Date | Status
|  |  | Regulation/Standard | Requirement ID | Verification Method
TASK-001 | Conduct initial risk assessment for project scope. | Jane Doe, Compliance Officer | ISO 27001 | RISK-27-A | Document review and audit log analysis. | 2024-05-15 | In Progress
TASK-002 | Review data handling procedures. | John Smith, Data Manager | GxP Guidelines (FDA 21 CFR Part 11) | PROC-44-B | Digital audit trail validation. | 2024-05-20 | Pending Approval
TASK-003 | Update access control policy. | Lisa Chen, IT Security Lead | NIST SP 800-53 (Rev. 4) | SEC-12-C | Policy document review and user testing. | 2024-05-18 | Completed
TASK-004 | Conduct employee training on compliance protocols. | Alex Rivera, HR Compliance | OHSAS 18001 (now ISO 45001) | TRAIN-33-D | Training attendance logs and quiz results. | 2024-05-22 | Not Started
TASK-005 | Schedule third-party audit for system security. | Maria Lopez, External Auditor Liaison | PCI DSS v4.0 | AUDIT-77-E | Independent audit report submission. | 2024-06-10 | Planned
TASK-006 | Document and file incident response plan. | Derek Brown, Risk Manager | <CERT Guidelines & GDPR Article 33 | RESP-19-F | Incident simulation results and documentation. | 2024-05-25 | In Progress