## Worksheet
Compliance Tracking - Project Plan (Startup Version)
Task ID | Task Description | Responsible Party | Start Date | Due Date | Status | Compliance Level(1-5)
T001 | Legal Entity Registration | CEO & Legal Team | 2024-04-01 | 2024-04-15 | Completed | 5
T002 | Data Protection Policy Drafting(GDPR/CCPA) | Compliance Officer | 2024-04-10 | 2024-05-15 | In Progress | 3
T003 | Security Audit Preparation(Penetration Testing) | IT Security Lead | 2024-05-15 | 2024-06-30 | Pending Start | 4
T004 | Employee Training on Compliance Protocols(Quarterly) | HR & Compliance Team | 2024-06-15 | 2024-07-31 | Pending Start | 5
T005 | Third-Party Vendor Compliance Review(SOC 2 & ISO 27001) | Legal & Procurement | 2024-07-15 | 2024-08-31 | Pending Start | 5
T006 | Final Compliance Audit & Reporting(Internal) | Compliance Officer & CFO | 2024-09-15 | 2024-10-31 | Pending Start | 5