## Worksheet
Task ID | Task Description | Responsible Team Member | Compliance Requirement | Status | Scheduled Start Date | Scheduled End Date | Actual Completion Date | Notes/Comments
T001 | Review regulatory guidelines for Q3 compliance. | Jane Smith | ISO 9001:2015 Section 4.3 | Pending | 2024-04-05 | 2024-04-15 |  | Review with Legal team before submission.
T002 | Conduct internal audit of documentation process. | Mike Johnson | OHSAS 18001:2007 Clause 7.5 | In Progress | 2024-04-16 | 2024-04-30 |  | Audit report to be reviewed by Compliance Manager.
T003 | Update employee training records for compliance. | Sarah Lee | ISO 14001:2015 Clause 7.2 | Not Started | 2024-05-01 | 2024-05-15 |  | Training must cover new environmental policies.
T004 | Submit compliance report to external auditor. | David Brown | NIST SP 800-53 Rev. 5, AC-6 | Pending Review | 2024-05-16 | 2024-05-31 |  | Final review by Legal and Finance.
Team Progress Summary
Total Tasks | 4 | Completed | 0 (0%) | In Progress | 1 (25%) | Pending Review | 1 (25%) | Not Started | 2 (50%)