## Worksheet
Week | Project Phase | Compliance Item | Status | Responsible Team | Due Date | Notes/Actions Required
Week 1 | Initiation | Licensing & Permits Review | Pending | Legal & Compliance | 2024-04-05 | Submit application to regulatory body.
Week 1 | Initiation | Data Privacy Assessment (GDPR/CCPA) | In Progress | Risk & Security Team | 2024-04-07 | Complete gap analysis and documentation.
Week 2 | Planning | Risk Management Plan Approval | Pending | Risk Management Office | 2024-04-12 | Review and sign-off by project sponsor.
Week 2 | Planning | Regulatory Compliance Checklist Completion | In Progress | Project Manager | 2024-04-14 | Cross-check all regulatory requirements.
Week 3 | Execution | Safety Compliance Training (All Staff) | Pending | HSE Department | 2024-04-19 | Conduct training sessions and track attendance.
Week 3 | Execution | Audit Readiness Preparation (Internal) | In Progress | Compliance Team | 2024-04-21 | Compile documentation and conduct mock audit.
Week 4 | Execution | Milestone Review: Phase 1 Compliance Validation | Pending | Project Steering Committee | 2024-04-26 | Evaluate compliance status and approve next phase.
Week 4 | Closure | Final Compliance Report Submission | Pending | Compliance Officer | 2024-04-30 | Draft and submit final report for stakeholder review.