## Worksheet
Compliance Tracking - Planning View
Project Template ¦ Status Overview & Milestone Planning
Compliance Item | Regulatory Standard | Responsible Team | Target Completion Date | Status (Planned) | Status (Actual) | Milestones & Progress(% Complete)
Data Privacy Compliance | GDPR, CCPA | Legal & IT Security | 2024-10-15 | In Progress | In Progress | 65%Phase 2 completed, Phase 3 in progress
Security Audit Readiness | ISO 27001 | IT Operations | 2024-11-30 | In Progress | Not Started | 15%Documentation review ongoing
Accessibility Compliance | WCAG 2.1 AA | Frontend Development | 2024-12-10 | In Planning | Not Started | 5%Initial audit scheduled for next week
Vendor Risk Assessment | SOX, NIST SP 800-53 | Risk Management Office | 2024-11-20 | In Planning | Not Started | 8%Vendor list compilation in progress
Internal Audit Schedule | COSO Framework | Internal Audit Team | 2025-01-31 | In Planning | Not Started | 3%Timeline draft underway
Last updated:April 27, 2024
Template Type: Project Template ¦ View Mode: Planning View