## Worksheet
Compliance Tracking - Weekly Project Template
Project Name: _________________________
Week of: _______________ ¦ Status: _______________
Item ID | Compliance Requirement | Responsible Party | Status (Not Started / In Progress / Completed) | Due Date | Actual Completion Date | Notes/Remarks
CR-001 | Data Privacy Policy Review | Jane Doe | In Progress | 2023-10-15 |  | Review draft version 2.1.
CR-002 | Security Audit Preparation | John Smith | Not Started | 2023-10-18 |  | No access to logs yet.
CR-003 | Employee Training Completion | Sarah Lee | Completed | 2023-10-14 | 2023-10-14 | All staff certified.
CR-004 | System Backup Verification | Marcus Brown | In Progress | 2023-10-16 |  | Last backup on 10/12, pending verification.
Total Items: 4 ¦ Completed: 1 ¦ In Progress: 2 ¦ Not Started: 1
Prepared by: _________________________ ¦ Date: _______________
Next Review Date: _______________ ¦ Approved By: _________________________