## Worksheet
Compliance Tracking - Project Timeline
Advanced Template ¦ Updated: May 23, 2024 ¦ Version 2.1
Phase | Task Description | Responsible Team | Due Date | Status | Compliance Level | Action Required
Planning & Initiation Phase
1 | Define project scope and compliance requirements | Project Management Office (PMO) | 2024-05-31 | Compliant | Audit Complete - 98%
1.1 | Identify regulatory standards (ISO, GDPR, HIPAA) | Legal & Compliance Team | 2024-06-05 | Compliant | Audit Complete - 100%
Development & Implementation Phase
2 | Implement data privacy controls (encryption, access logs) | IT Security Team | 2024-06-15 | In Progress | In Review - 85% | Verify encryption protocols
2.1 | Conduct internal security audit | Internal Audit Group | 2024-06-30 | Pending Review | Pending - 0% | Schedule audit meeting
Testing & Validation Phase
3 | Perform end-to-end compliance testing | QA & Compliance Unit | 2024-07-15 | Not Started | Pending - 0% | Allocate test resources
3.1 | Address non-conformance findings from testing | DevOps & Legal Team | 2024-07-25 | Not Started | Pending - 0% | Review test reports
Final Approval & Deployment Phase
4 | Secure sign-off from compliance committee | Compliance Officer | 2024-08-15 | Not Started | Pending - 0% | Request meeting with committee
4.1 | Deploy system to production environment | Operations Team | 2024-08-30 | Not Started | Pending - 0% | Finalize deployment checklist
Overall Compliance Rate: | [5 empty] | 89%
Note:Status colors indicate compliance progress. Green = Compliant, Yellow = In Progress/Warning, Red = Critical/Pending.