## Worksheet
Compliance Tracking - Project Timeline (Basic Version)
Task | Description | Responsible Party | Start Date | End Date | Status
Initiation Phase | Create project charter and compliance requirements document. | Project Manager | 2024-01-05 | 2024-01-15 | In Progress
Risk Assessment | Conduct initial risk analysis and compliance gaps evaluation. | Compliance Officer | 2024-01-16 | 2024-01-31 | In Progress
Policy Development | Draft internal compliance policies and procedures. | Legal & Compliance Team | 2024-02-01 | 2024-03-15 | Pending
Training & Awareness | Conduct employee training sessions on compliance standards. | HRTeam | 2024-03-16 | 2024-04-15 | Pending
Internal Audit | Perform internal audit to ensure policy adherence. | Audit Team | 2024-04-16 | 2024-05-31 | Pending
External Certification | Engage external auditor for compliance certification. | Compliance Officer | 2024-06-01 | 2024-07-31 | Pending
Closure & Reporting | Finalize project documentation and submit compliance report. | Project Manager | 2024-08-01 | 2024-08-31 | Pending
Note: This table is designed to reflect a basic compliance tracking template for a project timeline. Update status as milestones are completed.