## Worksheet
Compliance Tracking - Project Timeline (Business Use)
Task ID | Activity Description | Responsible Party | Start Date | Due Date | Status | Compliance Level
TASK001 | Regulatory Risk Assessment Review | Legal & Compliance Team | 2024-01-15 | 2024-01-31 | Completed | Full Compliance
TASK002 | Data Privacy Audit (GDPR/CCPA) | IT Security Division | 2024-01-18 | 2024-02-15 | In Progress | Partially Compliant
TASK003 | Internal Policy Documentation Update | HR & Legal Department | 2024-01-25 | 2024-02-10 | Completed | Full Compliance
TASK004 | Third-party Vendor Compliance Verification | Procurement & Risk Team | 2024-02-01 | 2024-03-15 | Overdue | Pending Review
TASK005 | Annual Compliance Training Completion (All Staff) | Training & Development Unit | 2024-02-15 | 2024-03-31 | In Progress | In Progress (85%)
TASK006 | Certification Renewal Submission (ISO 27001) | Compliance Manager | 2024-03-01 | 2024-04-30 | Planned | Pending Initiation
Last updated on:April 5, 2024¦ Prepared for Business Use – Compliance Tracking Dashboard