## Worksheet
Compliance Tracking - Project Timeline (Client View)
Phase / Milestone | Responsible Team | Scheduled Start | Scheduled End | Actual Completion | Status | Compliance Requirement ID
Project Initiation & Planning | Project Management Office | 2023-10-01 | 2023-10-15 | 2023-10-14 | Compliant | CRQ-2023-PJCT-001
Regulatory Requirements Assessment | Compliance & Legal Team | 2023-10-16 | 2023-10-31 |  | Approaching Deadline | CRQ-2023-PJCT-005
Data Privacy & Security Implementation | IT & Security Team | 2023-11-01 | 2023-11-30 |  | Overdue | CRQ-2023-PJCT-012
Third-Party Vendor Onboarding | Procurement & Legal Team | 2023-11-05 | 2023-11-20 |  | Compliant | CRQ-2023-PJCT-018
Internal Testing & Validation | Quality Assurance Team | 2023-12-01 | 2023-12-15 |  | Compliant | CRQ-2023-PJCT-034
Final Compliance Audit & Sign-off | Internal Audit Team | 2023-12-16 | 2023-12-31 |  | Compliant | CRQ-2023-PJCT-045
Total Compliance Items: 6 ¦ Compliant: 4 ¦ At Risk: 1 ¦ Overdue: 1
Legend:
Compliant– Requirement met on or before deadline
Approaching Deadline– Completion expected within 5 days
Overdue– Deadline has passed without completion