## Worksheet
Compliance Tracking - Daily Project Timeline
Task ID | Task Description | Responsible Team | Start Date | Planned End Date | Daily Status (DD/MM/YYYY) | Last Updated
CT-001 | Review Regulatory Requirements | Compliance Team | 01/04/2025 | 05/04/2025 | On Track | 03/04/2025
CT-002 | Conduct Internal Audit Prep | Audit Department | 03/04/2025 | 10/04/2025 | Completed (Actual) | 11/04/2025
CT-003 | Update Documentation Standards | Documentation Unit | 05/04/2025 | 15/04/2025 | Delayed (Pending Review) | 13/04/2025
CT-004 | Train Staff on New Compliance Protocols | HR & Training | 12/04/2025 | 18/04/2025 | On Track | 13/04/2025
CT-005 | Submit Compliance Report to Regulator | Compliance Team | 16/04/2025 | 23/04/2025 | On Track | 13/04/2025
Daily Status Update Log:All entries updated daily at the close of business. Status reflects current progress as of the Last Updated date.