## Worksheet
Project Phase | Compliance Requirement | Timeline & Milestones |  |  | Responsible Party | Status | Notes/Remarks
|  | Start Date | Due Date | Actual Completion Date
Phase 1: Initial Planning & Compliance Assessment
Project Initiation | Define project scope and compliance objectives | 2024-04-01 | 2024-04-15 |  | Jane Doe (PM) | In Progress | Review regulatory standards for industry.
Risk Assessment | Conduct internal compliance risk analysis | 2024-04-16 | 2024-05-10 |  | John Smith (Compliance Officer) | Pending Review | Risk matrix to be submitted for executive approval.
Phase 2: Policy Development & Implementation
Policy Drafting | Develop compliance policies aligned with regulations (e.g., GDPR, HIPAA) | 2024-05-11 | 2024-06-15 |  | Legal Team Lead | In Progress | Policies under review by internal audit.
Employee Training Program Setup | Create training modules for compliance awareness | 2024-06-16 | 2024-07-31 |  | L&D Coordinator | Pending Start | Content development underway.
Phase 3: Monitoring, Audit & Reporting
Internal Audit Preparation | Prepare documentation and evidence for audit readiness | 2024-08-01 | 2024-09-15 |  | Audit Manager (Internal) | Pending Start | All departments to submit compliance records.
External Audit Execution | Conduct third-party audit for validation | 2024-09-16 | 2024-10-31 |  | Audit Firm XYZ | Not Started | Audit contract signed on 08/25.
Phase 4: Continuous Compliance & Review
Compliance Dashboard Setup | Implement real-time tracking system for compliance indicators | 2024-11-01 | 2025-01-31 |  | IT Compliance Team | Pending Start | Built using Power BI integration.
Quarterly Compliance Review | Conduct formal review and update policies as needed | 2025-01-01 | 2025-03-31 |  | Compliance Committee | Pending Start | Annual compliance cycle begins.
Total Tasks: | [6 empty] | 8
On Track: | [6 empty] | 3
Delayed/At Risk: | [6 empty] | 3