## Worksheet
Compliance Tracking - Project Timeline (Extended)
Phase | Task Description | Responsible Party | Start Date | Due Date | Status | Compliance Level(1-5) | Documentation Link(if applicable)
Phase 1: Planning | Define project scope and objectives | Project Manager | 2024-01-05 | 2024-01-15 | Compliant | 5 | Doc 1 - Scope.pdf
| Identify compliance requirements (ISO, GDPR, etc.) | Compliance Officer | 2024-01-10 | 2024-01-25 | Compliant | 5 | Doc 2 - Req Analysis.xlsx
| Develop compliance risk assessment matrix | Risk Analyst | 2024-01-18 | 2024-01-30 | Compliant | 4.5 | Doc 3 - Risk Matrix.docx
Phase 2: Development | Design system architecture with compliance controls | Lead Architect | 2024-02-01 | 2024-03-15 | Compliant | 5 | Doc 4 - Arch Design.pdf
| Implement data encryption and access controls | Security Engineer | 2024-03-16 | 2024-05-31 | Compliant | 5 | Doc 5 - Security Setup.txt
| Conduct internal code review for regulatory standards | Senior Developer | 2024-05-01 | 2024-06-15 | Compliant | 4.8 | Doc 6 - Code Review Report.docx
| Perform penetration testing and vulnerability scan | Cybersecurity Team | 2024-06-16 | 2024-07-31 | Compliant | 5 | Doc 7 - Pen Test Results.pdf
Phase 3: Validation | Conduct compliance audit with third-party auditor | Auditor (External) | 2024-08-01 | 2024-08-31 | Compliant | 5 | Doc 8 - External Audit.pdf
| Address audit findings and remediation actions | Compliance Team | 2024-09-01 | 2024-10-31 | Compliant | 5 | Doc 9 - Remediation Log.xlsx
Phase 4: Deployment | Deploy system to production environment | DevOps Engineer | 2024-11-01 | 2024-11-30 | Compliant | 5 | Doc 10 - Deployment Logs.txt
| Post-deployment compliance monitoring setup | Operations Manager | 2024-12-01 | 2024-12-31 | Compliant | 5 | Doc 11 - Monitoring Config.pdf
Phase 5: Review & Close | Final compliance review and sign-off | Project Sponsor | 2025-01-01 | 2025-01-31 | Compliant | 5 | Doc 12 - Final Sign-off.pdf
| Archive all compliance documentation for audit trail | Records Manager | 2025-02-01 | 2025-02-15 | Compliant | 4.9 | Doc 13 - Archive Index.xlsx
Total Compliance Score: |  |  |  |  | 4.87 | 13.5 (avg)
This table is a compliance tracking template for project timelines. All dates are in YYYY-MM-DD format. Status indicators:Compliant- On time, fully compliantApproaching Due- Within 7 days of due dateOverdue- Past due date.