## Worksheet
Compliance Tracking - Project Timeline
# | Project Phase / Task | Responsible Party | Timeline |  |  | Compliance Status
|  |  | Start Date | Due Date | Actual Completion
1 | Regulatory Requirements Assessment | Legal & Compliance Team | 2024-03-01 | 2024-03-15 |  | Pending
2 | Data Privacy Impact Assessment (DPIA) | Data Protection Officer | 2024-03-16 | 2024-03-31 |  | Pending
3 | System Architecture Review for Compliance | IT Security Team | 2024-04-01 | 2024-04-15 |  | Pending
4 | Policy & Procedure Documentation Finalization | Compliance Manager | 2024-04-16 | 2024-05-10 |  | Pending
5 | Internal Audit & Gap Analysis | Audit Team Lead | 2024-05-11 | 2024-06-30 |  | Pending
6 | Risk Mitigation Plan Implementation | Risk Manager | 2024-07-01 | 2024-08-15 |  | Pending
7 | Third-Party Vendor Compliance Review | Procurement & Legal | 2024-08-16 | 2024-09-30 |  | Pending
8 | Final Compliance Certification Submission | Compliance Office | 2024-10-01 | 2024-10-31 |  | Pending
9 | Regulatory Submission Approval & Reporting | CERT Compliance Team | 2024-11-01 | 2024-11-30 |  | Pending
10 | Post-Implementation Review & Lessons Learned | Project Manager | 2024-12-01 | 2024-12-31 |  | Pending