## Worksheet
Task/Activity | Responsible Party | Start Date | Due Date | Status | Compliance Requirement
Initial Compliance Assessment | Jane Doe | 2024-01-05 | 2024-01-15 | In Progress | ISO 9001:2015 Clause 4.3
Documentation Review & Update | John Smith | 2024-01-16 | 2024-01-31 | Pending | ISO 9001:2015 Clause 7.5
Internal Audit Planning | Sarah Lee | 2024-02-01 | 2024-02-15 | Not Started | ISO 9001:2015 Clause 9.2
Employee Training Session | Mike Brown | 2024-02-16 | 2024-02-18 | Pending | OHSAS 18001:2007 Clause 6.3
External Audit Preparation | Lisa Wong | 2024-02-19 | 2024-03-15 | Pending | ISO 9001:2015 Clause 9.3
Audit Execution & Reporting | Robert Taylor | 2024-03-16 | 2024-04-15 | Pending | ISO 9001:2015 Clause 9.3.2
Corrective Action Implementation | Jane Doe | 2024-04-16 | 2024-05-15 | Pending | ISO 9001:2015 Clause 10.3
Final Compliance Review & Sign-off | Executive Team | 2024-05-16 | 2024-05-31 | Pending | All Applicable Standards
Notes:This template is for personal use and may be customized for specific compliance requirements. Status updates should be reviewed weekly.