## Worksheet
Compliance Tracking - Project Timeline (Planning View)
Task ID | Compliance Item | Responsible Team/Person | Start Date | End Date | Status (Planned) | Milestone?
CT-001 | Regulatory Document Submission | Legal & Compliance Team | 2024-04-01 | 2024-05-15 | In Progress | Yes
CT-002 | Data Privacy Audit (GDPR) | IT Security Team | 2024-05-16 | 2024-06-30 | Not Started | Yes
CT-003 | Safety Certification (ISO 45001) | Operations Department | 2024-07-01 | 2024-08-31 | Not Started | Yes
CT-004 | Environmental Impact Assessment (EIA) | Sustainability Office | 2024-09-01 | 2024-11-30 | Not Started | Yes
CT-005 | Certification Review & Approval | Compliance Oversight Board | 2024-12-01 | 2025-01-31 | Not Started | Yes
CT-006 | Annual Compliance Training (All Staff) | Hr & L&D Team | 2025-01-15 | 2025-03-31 | Not Started | No
CT-007 | Third-Party Vendor Compliance Check | Procurement & Legal | 2025-04-01 | 2025-06-30 | Not Started | No
Note:This is a planning view template for compliance tracking. Actual progress may vary.