## Worksheet
Compliance Tracking - Project Timeline Report
Project:Compliance Enhancement Initiative
Date Generated:May 5, 2024
# | Task/Activity | Responsible Party | Start Date | End Date | Status | Compliance Requirement ID
1 | Policy Review & Documentation Update | Laura Mitchell, Compliance Officer | 2024-04-01 | 2024-04-15 | Compliant | CMP-RQ-2023-115
2 | Employee Training Program Rollout | Daniel Reyes, HR Manager | 2024-04-16 | 2024-05-10 | In Progress | CMP-RQ-2023-118
3 | Internal Audit Preparation | Sarah Chen, Audit Lead | 2024-05-01 | 2024-05-15 | In Progress | CMP-RQ-2023-119
4 | Data Privacy Assessment & Remediation | James Park, IT Security | 2024-05-16 | 2024-06-30 | Non-Compliant | CMP-RQ-2023-121
5 | Regulatory Reporting Submission (Q1) | Victoria Liu, Regulatory Affairs | 2024-06-01 | 2024-06-30 | Compliant
Legend:
Compliant– Requirement fully met
In Progress– Ongoing with expected completion within timeline
Non-Compliant– Not yet met; requires immediate action and follow-up