## Worksheet
Task | Responsible Party | Start Date | End Date | Status | Compliance Requirement
Initial Risk Assessment | Compliance Officer | 2024-01-05 | 2024-01-15 | In Progress | ISO 37301 Clause 6.1.2
Policy Development | Legal Team | 2024-01-16 | 2024-01-31 | Not Started | ISO 37301 Clause 7.2.1
Employee Training Session | HR Department | 2024-02-01 | 2024-02-15 | Not Started | ISO 37301 Clause 7.3.1
Internal Audit Preparation | Audit Team | 2024-02-16 | 2024-03-01 | Not Started | ISO 37301 Clause 9.2
External Audit Engagement | Compliance Officer | 2024-03-05 | 2024-03-15 | Not Started | ISO 37301 Clause 9.3
Corrective Action Implementation | Project Manager | 2024-03-16 | 2024-04-15 | Not Started | ISO 37301 Clause 10.2
Final Compliance Review | Senior Management | 2024-04-16 | 2024-05-01 | Not Started | ISO 37301 Clause 9.4