## Worksheet
Compliance Tracking - Project Timeline (Summary View)
Project Phase | Start Date | End Date | Status | Compliance Level | Responsible Team | Notes / Exceptions
Planning & Initiation | 2024-01-05 | 2024-01-19 | Completed | High | Project Management Office (PMO) | No deviations observed.
Regulatory Review | 2024-01-20 | 2024-02-15 | In Progress | High | Legal & Compliance Team | Final documentation submitted on 2024-01-31.
Design & Development | 2024-02-16 | 2024-04-30 | In Progress | Medium-High | Development Team | Scheduled code reviews every Friday.
Testing & Validation | 2024-05-01 | 2024-06-15 | On Hold (Pending Compliance Approval) | High | QA Team | Waiting for final sign-off from Legal.
Deployment Preparation | 2024-06-16 | 2024-07-15 | Pending | High | Operations & IT Team | Infrastructure readiness confirmed.
Production Rollout | 2024-07-16 | 2024-08-31 | Pending | High | Deployment Team | Scheduled in phases across regions.
Total Duration | 2024-01-05 to 2024-08-31 (270 days)
Legend:
Completed / In Progress- On schedule and compliant.
On Hold / Delayed- Requires attention or approval.
Exception- Non-compliance reported with mitigation plan.