## Worksheet
Compliance Tracking - Project Timeline (Team Use)
Task ID | Task Description | Responsible Team Member | Start Date | Due Date | Status | Milestones & Notes
T001 | Regulatory Document Review | Legal Team | 2024-04-05 | 2024-04-15 | In Progress | Preliminary draft reviewed by Compliance Officer.
T002 | Internal Audit Preparation | Audit Team | 2024-04-10 | 2024-05-15 | Not Started | Data collection phase begins.
T003 | Employee Training Session - Compliance | HR Department | 2024-05-18 | 2024-05-31 | Pending Approval | Scheduled for all departments.
T004 | External Audit Coordination | Compliance Manager | 2024-06-15 | 2024-07-31 | Not Started | Pending vendor confirmation.
T005 | Final Compliance Report Submission | Compliance Team | 2024-08-15 | 2024-09-15 | Pending Approval | All prior tasks must be completed.
Project Progress Summary
Total Tasks: |  |  | 5 |  | Completed: 0 / In Progress: 1 / Not Started: 3
Status Legend
In Progress– Task is actively being worked on. Pending Approval– Awaiting review or confirmation. Not Started– Task has not yet begun.