## Worksheet
Week | Start Date | End Date | Task/Activity | Responsible Person | Status (✓/✗) | Compliance Requirement | Notes
Week 1 | 2024-04-01 | 2024-04-07 | Initial Compliance Assessment | Jane Doe |  | CERT-A1, ISO 9001:2015 Clause 8.5.1 | Review existing documentation and processes.
Week 2 | 2024-04-08 | 2024-04-14 | Update SOPs for Regulatory Standards | John Smith |  | FDA 21 CFR Part 820, GDPR Art. 33 | SOPs to be reviewed and updated by compliance team.
Week 3 | 2024-04-15 | 2024-04-21 | Team Training on Compliance Updates | Alice Brown |  | OHSAS 18001, ISO/IEC 27001:2013 | Training scheduled for April 18th; attendance tracked.
Week 4 | 2024-04-22 | 2024-04-28 | Internal Audit Preparation | Robert Lee |  | ISO 13485, SOX Section 404 | Gather evidence, check forms and records.
Week 5 | 2024-04-29 | 2024-05-05 | Conduct Internal Audit | Linda Chen |  | All applicable standards | Report to be submitted by May 6.
Week 6 | 2024-05-06 | 2024-05-12 | Closure of Non-Conformities Identified | Michael Taylor | N/A | Corrective Actions Completed by May 10.
End of Tracking Period – Review and Plan for Next Cycle