## Worksheet
Compliance Tracking Schedule Planner (Detailed)
ID | Regulation / Standard | Department Responsible | Schedule & Deadlines |  |  |  | Due Date | Next Review Date | Status | Last Updated By
|  |  | Planned Start | Target Completion | Actual Completion | Extensions (Days)
R-001 | GDPR Compliance – Data Processing Agreements | Legal & Privacy Office | 2024-03-15 | 2024-05-31 | 2024-05-18 | 7 | 2024-06-30 | 2025-11-30 | Compliant | Jane Smith
R-002 | ISO 27001:2022 – Internal Audit Preparation | IT Security Team | 2024-04-15 | 2024-11-30 |  |  | Pending Review
R-003 | SOX Compliance – Financial Controls Testing | Finance & Audit Department | 2024-01-15 | 2024-10-31 |  |  | Overdue (68 Days)
R-004 | CCPA – Consumer Rights Request Process | Customer Support & Legal | 2024-06-15 | 2024-11-30 | Compliant (Partial)
R-005 | OHSAS 18001 – Workplace Safety Review | Human Resources & Safety Office | 2024-03-15 | Compliant (Final)
R-006 | HIPAA – Access Control Audit | IT & Healthcare Compliance | In Progress (45%)
R-007 | PCI DSS – Quarterly Scanning & Reporting | Payment Systems Team | Overdue (42 Days)
R-008 | GDPR – Data Subject Access Requests (DSARs) | Privacy & Legal | Compliant
R-009 | FCC Regulations – Network Reporting (Quarterly) | Telecom Operations | In Progress (25%)
R-010 | Cal/OSHA – Annual Safety Training Completion | HR & Facilities Management | Compliant (Pending Verification)
Total Active Items: |  |  |  |  | 10 | Compliant: |  | 4 | Overdue: | Pending/In Progress:
Legend:Compliant (Green), Overdue (Red), Warning/In Progress (Orange)