## Worksheet
Compliance Tracking - Detailed To-Do List
Task ID | Description | Regulatory Standard | Responsible Party | Due Date | Status | Priority | Action Items/Notes
CPL-001 | Conduct annual security audit for all systems handling PII data. | GDPR Article 32, HIPAA Security Rule 164.312 | IT Security Team | 2025-04-15 | In Progress | High | Initial assessment scheduled for Mar 18. Review findings by Apr 1.
CPL-002 | Update privacy policy to reflect new data processing activities. | GDPR Article 13, CCPA § 1798.135 | Legal & Compliance Department | 2025-04-30 | Pending | Medium | Need review from marketing team prior to finalization.
CPL-003 | Train all employees on updated data handling procedures. | ISO 27001:2022, OSHA 1910.120 | HR Training Division | 2025-05-14 | Pending | High | Scheduled workshop on Apr 30. Materials in draft form.
CPL-004 | Implement MFA for all remote access accounts. | ISO 27001:2022, NIST SP 800-63B | Network Operations Team | 2025-04-18 | In Progress | High | Rollout completed for 60% of users. Testing phase ongoing.
CPL-005 | Document and validate third-party vendor compliance. | SOX Section 404, GDPR Art. 28 | Procurement & Legal Team | 2025-06-30 | Pending | Medium | Vendor assessment forms sent out Mar 14. Follow-up required.
CPL-006 | Review and update incident response plan with recent breach scenarios. | NIST SP 800-61 Rev. 2, ISO 27035 | Incident Response Team | 2025-04-19 | Completed | High | Plan updated and approved on Apr 17. Training sessions scheduled.
Legend:
Pending– Task not started or waiting on input.
In Progress– Task currently being worked on.
Completed– Task finished and verified.