## Worksheet
Task | Start Date | End Date | Duration (Days) | Status | Owner | Progress Bar
Content Calendar Setup | 2024-06-01 | 2024-06-05 | 5 | Completed | Marketing Team
Blog Post Series - Q3 | 2024-06-10 | 2024-08-30 | 82 | In Progress | Content Writers
Social Media Campaigns | 2024-06-15 | 2024-09-15 | 93 | Not Started | Social Media Team
Video Content Production | 2024-07-01 | 2024-08-15 | 46 | Delayed | Production Team
Email Newsletter Redesign | 2024-07-20 | 2024-08-10 | 22 | Completed | Digital Team
SEO Optimization Audit | 2024-06-20 | 2024-07-15 | 26 | Completed | SEO Specialists