## Worksheet
Task Name | Start Date | End Date | Duration (Days) | Progress (%) | Owner | Dependencies | Status | Gantt Bar
Content Research | 2024-06-01 | 2024-06-05 | 5 | 100 | Alice Smith | None | Completed
Outline Creation | 2024-06-06 | 2024-06-08 | 3 | 85 | Bob Johnson | Content Research | In Progress
Draft Writing | 2024-06-09 | 2024-06-15 | 7 | 50 | Carol White | Outline Creation | In Progress
Edit & Review | 2024-06-16 | 2024-06-20 | 5 | 15 | David Brown | Draft Writing | Not Started
Publish & Promote | 2024-06-21 | 2024-06-25 | 5 | 0 | Eve Davis | Edit & Review | Not Started