## Worksheet
Task | Start Date | End Date | Duration (Days) | Progress (%) | Owner | Status | Gantt Bar
Content Research | 2024-06-01 | 2024-06-05 | 5 | 100% | Jane Doe | Completed
Outline Creation | 2024-06-06 | 2024-06-10 | 5 | 80% | John Smith | In Progress
Content Writing | 2024-06-11 | 2024-06-20 | 10 | 30% | Alex Brown | Not Started
Editorial Review | 2024-06-21 | 2024-06-25 | 5 | 0% | Lisa Green | Not Started
Publish & Promote | 2024-06-26 | 2024-06-30 | 5 | 0% | Mike White | Not Started