## Worksheet
Task ID | Task Name | Category | Owner | Start Date | End Date | Status | Priority | Dependencies | Notes
T001 | Research Target Audience | Content Research | Jane Doe | 2024-06-01 | 2024-06-05 | Completed | High | None | Use survey data from Q1.
T002 | Create Editorial Calendar | Planning | John Smith | 2024-06-06 | 2024-06-12 | In Progress | High | T001 | Align with seasonal campaigns.
T003 | Draft Blog Posts (Q3) | Content Creation | Alex Rivera | 2024-06-13 | 2024-06-25 | Not Started | Medium | T002 | Include SEO keywords from research.
T004 | Design Social Media Graphics | Visual Content | Mira Chen | 2024-06-15 | 2024-06-28 | Not Started | Medium | T003 | Use brand template pack v3.
T005 | Publish Content & Analyze Metrics | Distribution & Analysis | Chris Lee | 2024-06-26 | 2024-07-15 | Not Started | High | T003, T004 | Track CTR, shares, conversions.