## Worksheet
Task Name | Start Date | End Date | Status | Owner | Priority | % Complete
Content Research | 2024-06-01 | 2024-06-05 | Completed | Alex Morgan | High | 100%
Outline Creation | 2024-06-06 | 2024-06-10 | In Progress | Jamal Lee | High | 75%
Draft Writing | 2024-06-11 | 2024-06-18 | Not Started | Sarah Chen | Medium | 0%
Visual Assets Design | 2024-06-12 | 2024-06-15 | Not Started | Taylor Kim | Medium | 0%
Review & Edits | 2024-06-19 | 2024-06-22 | Not Started | Alex Morgan | High | 0%
Publish & Promote | 2024-06-23 | 2024-06-25 | Not Started | Jamal Lee | Low | 0%