## Worksheet
Task ID | Task Name | Owner | Start Date | End Date | Status | Priority | Dependencies | Notes
1 | Content Audit | Marketing Team | 01/01/2024 | 07/01/2024 | Completed | High | None | Review all existing content across platforms.
2 | Content Strategy Development | Content Director | 08/01/2024 | 14/01/2024 | In Progress | High | 1 | Align with Q1 business goals and audience personas.
3 | Content Calendar Creation | Content Coordinator | 15/01/2024 | 21/01/2024 | Not Started | Medium | 2 | Include social, blog, email, and video content.
4 | Content Creation (Phase 1) | Writers & Designers | 22/01/2024 | 04/02/2024 | Not Started | High | 3 | Produce first set of blog posts and graphics.
5 | Content Review & Approval | Legal & Compliance | 05/02/2024 | 11/02/2024 | Not Started | Medium | 4 | Ensure brand and regulatory compliance.
6 | Content Publishing | Digital Team | 12/02/2024 | 18/02/2024 | Not Started | High | 5 | Schedule and deploy across all channels.
7 | Performance Tracking & Reporting | Analytics Team | 19/02/2024 | 25/02/2024 | Not Started | Low | 6 | Measure KPIs and prepare executive summary.