## Worksheet
Date | Task | Responsible Person | Estimated Cost | Actual Cost | Variance (Actual - Estimated) | Status
2024-04-01 | Material Procurement | John Doe | $5,000.00 | $4,850.00 | $-150.00 (Under Budget) | Completed
2024-04-05 | Labor Allocation Review | Jane Smith | $7,500.00 | $7,625.00 | +$125.00 (Over Budget) | On Track
2024-04-10 | Equipment Maintenance | Mike Johnson | $3,200.00 | $3,150.00 | -$50.00 (Under Budget) | Completed
2024-04-15 | Supply Chain Audit | Sarah Lee | $6,800.00 | $7,100.00 | +$300.00 (Over Budget) | On Hold
Total Estimated Cost: |  |  |  | $22,500.00 | $22,725.00 | Total Variance:
Total Overrun: |  |  |  | $225.00 |  | + $225.00