## Worksheet
Client Name | Project Title | Start Date | End Date | Budget (USD) | Actual Spend (USD) | Variance (USD) | Status | Cost Control Review Date | Next Action
Alpha Innovations Inc. | Cloud Migration Project | 2023-04-15 | 2023-09-30 | 150,000.00 | 138,567.25 | +11,432.75 (Under Budget) | On Track | 2023-06-10 | Review resource allocation
Bright Solutions Ltd. | UI/UX Redesign | 2023-05-01 | 2023-08-15 | 75,000.00 | 78,245.60 | -3,245.60 (Over Budget) | At Risk | 2023-07-15 | Adjust scope and reallocate funds
Global Reach Enterprises | ERP Implementation | 2023-03-10 | 2024-01-31 | 500,000.00 | 467,892.35 | +32,107.65 (Under Budget) | On Track | 2023-09-05 | Update progress report and forecast
Nova Tech Services | API Integration Phase 2 | 2023-06-20 | 2023-11-30 | 95,000.00 | 98,765.43 | -3,765.43 (Over Budget) | At Risk | 2023-08-25 | Conduct cost audit and revise timeline