## Worksheet
Client Name | Project Title | Start Date | End Date | Budget (USD) | Actual Spend (USD) | Variance (%) | Status | Cost Control Actions
Alpha Solutions Inc. | Web Platform Development | 2023-04-15 | 2023-08-31 | $150,000 | $138,500 |  | +7.6% | On Track | Monthly reviews; budget reallocation approved
Global Innovations Ltd. | Cloud Migration Project | 2023-05-01 | 2023-11-30 | $250,000 | $268,750 | -7.5% | Over Budget | Immediate audit; revised timeline and scope proposed
NextGen Tech Co. | Mobile App Redesign | 2023-06-10 | 2023-10-15 | $95,000 | $87,340 | +8.4% | On Track | Weekly cost monitoring; no changes required
Digital Edge Partners | Data Analytics Implementation | 2023-07-05 | 2023-12-31 | $180,000 | $195,600 | -8.6% | Over Budget | Cost escalation reviewed; vendor renegotiation in progress