## Worksheet
Client Name | Project Title | Start Date | End Date | Budget (USD) | Actual Spend (USD) | Variance (USD) | Status | Cost Control Action
Alpha Innovations Inc. | AI Integration Platform | 2023-04-15 | 2024-03-31 | $750,000 | $689,500 | $60,500 (Under) | On Track | Monthly review and forecast update
Beta Solutions Ltd. | Cloud Migration Initiative | 2023-06-01 | 2024-11-30 | $500,000 | $495,250 | $4,750 (Under) | On Track | Resource reallocation approved
Gamma Tech Partners | Data Analytics Dashboard | 2023-08-10 | 2024-06-15 | $350,000 | $375,800 | -$25,800 (Over) | At Risk | Additional review and cost reduction plan in progress
Delta Systems Group | Mobile App Development | 2023-03-05 | 2024-12-31 | $1,000,000 | $945,675 | $54,325 (Under) | On Track | Cost monitoring every 3 weeks