## Worksheet
Date | Client Name | Project Title | Estimated Cost | Actual Cost | Variance (Actual - Estimated) | Status | Notes
2024-04-01 | Alpha Solutions Inc. | Website Redesign | $15,000 | $13,850 | -$1,150 (Under Budget) | On Track | Design finalized; development on schedule.
2024-04-10 | Beta Systems Ltd. | ERP Integration | $35,000 | $38,200 | +$3,200 (Over Budget) | At Risk | Delay in third-party API delivery.
2024-04-15 | Gamma Innovations | Mobile App Development | $28,000 | $27,950 | -$50 (Under Budget) | On Track | No major deviations; testing completed.
2024-04-20 | Delta Technologies | Data Migration | $18,500 | $19,750 | +$1,250 (Over Budget) | Delayed | Unplanned server downtime caused delays.