## Worksheet
Date | Customer Name | Project/Opportunity | Estimated Cost | Actual Cost | Variance (Actual - Estimated) | Cost Control Status | Approval Required? | Notes
2024-04-01 | GlobalTech Inc. | Cloud Migration Project | $50,000 | $48,500
2024-04-15 | NexGen Solutions | CRM Integration Setup | $35,000 | $37,200 | +$2,200 (Over budget) | Under Review | Yes | Additional third-party licensing required.
2024-05-03 | Alpha Enterprise | Data Analytics Dashboard | $60,000 | $59,800 | -$200 (Under budget) | On Track | No | Minor scope adjustment approved.
2024-05-18 | SmartFlow Systems | API Development Phase | $75,000 | $82,500 | +$7,500 (Over budget) | At Risk | Yes | Scope creep identified; requires re-estimation.