## Worksheet
Date | Client Name | Project | Estimated Cost | Actual Cost | Variance (Actual - Estimated) | Status | Notes
2024-04-01 | GreenTech Solutions | Website Redesign | $5,000.00 | $4,850.00 | -$150.00 | On Track | Delivered on time with minor scope reduction.
2024-04-15 | Nexus Analytics | Data Migration Service | $8,500.00 | $9,200.00 | +$700.00 | Over Budget | Additional data cleaning required; timeline extended.
2024-04-22 | Sunny Marketing | Content Strategy Workshop | $3,000.00 | $3,150.00 | +$150.00 | Over Budget | Extended sessions due to client feedback.
2024-05-03 | Flyer Design Studio | Brand Identity Package | $6,200.00 | $6,180.00 | -$20.00 | On Track | No changes; delivered as planned.