## Worksheet
Date | Client Name | Project Name | Estimated Cost | Actual Cost | Variance (Actual - Estimated) | Status | Remarks
2024-04-01 | ABC Corp | Website Redesign | $15,000 | $13,500 | -$1,500 (Under Budget) | In Progress | Design phase completed on time.
2024-04-15 | XYZ Ltd | CRM System Setup | $25,000 | $28,750 | +$3,750 (Over Budget) | On Hold | Additional integrations requested.
2024-04-20 | Nexus Solutions | Mobile App Development | $30,000 | $30,000 | $0 (On Budget) | Completed | All milestones achieved.
2024-05-03 | GlobalTech Inc | Data Migration Project | $18,000 | $19,200 | +$1,200 (Over Budget) | Delayed | Unexpected data complexity.
Total Estimated Cost |  |  |  | $88,000 |  | Total Actual Cost
Overall Variance |  |  |  | $1,950 (Over Budget) |  | Action Required