## Worksheet
Date | Client Name | Project Name | Estimated Cost | Actual Cost | Variance (Actual - Estimated) | Status | Action Taken
2024-03-15 | AlphaTech Solutions | ERP System Upgrade | $45,000 | $42,800 | -$2,200 (Under Budget) | On Track | Monthly review conducted; no escalation.
2024-03-20 | GreenField Innovations | Customer Portal Launch | $38,500 | $41,750 | +$3,250 (Over Budget) | At Risk | Resource reallocation requested; additional review in 3 days.
2024-03-25 | NexaCorp Ltd | Marketing Automation Setup | $29,000 | $29,000 | $0 (On Budget) | Complete | Final invoice approved and closed.
Summary Statistics |  |  |  |  | Total Variance = $-1,500 | Budget Health = 92% | Next Review Date: 2024-04-05