## Worksheet
Date | Client/Project | Budget Allocation | Actual Spend | Variance (Actual - Budget) | Status | Remarks
2024-04-01 | Acme Corp - Website Redesign | $15,000 | $13,200 |  | $1,800 Under Budget | On Track | Design phase completed early.
2024-04-15 | Global Tech - App Development | $30,000 | $28,500 | $1,500 Under Budget | On Track | Development progressing smoothly.
2024-04-20 | Northstar Inc - Marketing Campaign | $10,000 | $12,300 | $2,300 Over Budget | At Risk | Unapproved ad spend increase.
2024-04-25 | Sunrise Solutions - Client Onboarding | $8,000 | $7,600 | $400 Under Budget | <On Track | Streamlined process reduced costs.