## Worksheet
Activity | Start Date | End Date | Duration (Days) | Cost Estimate ($) | Responsible Party | Status
Annual Budget Review | Jan 1, 2024 | Jan 15, 2024 | 15 | 5,000 | Finance Department | On Track
Vendor Cost Audit | Jan 16, 2024 | Feb 5, 2024 | 19 | 8,500 | Procurement Team | In Progress
Operational Expense Forecasting | Feb 6, 2024 | Mar 10, 2024 | 35 | 12,000 | Operations Team | Planned
Capital Spend Approval | Mar 11, 2024 | Apr 30, 2024 | 60 | 35,000 | Finance & Compliance | Pending Review
Annual Cost Variance Analysis | May 1, 2024 | May 31, 2024 | 31 | 7,500 | Audit Committee | Scheduled
Resource Reallocation Planning | Jun 1, 2024 | Jul 15, 2024 | 45 | 9,800 | HR & Operations | Planned