## Worksheet
Task | Start Date | End Date | Duration (Days) | Status | Cost (USD) | Responsible
Project Initiation | 2024-03-01 | 2024-03-15 | 15 | Completed | 5,000 | Project Manager
Requirements Gathering | 2024-03-16 | 2024-04-10 | 35 | In Progress | 12,000 | Business Analysts
Design Phase | 2024-04-11 | 2024-05-15 | 45 | Planned | 20,000 | UX & UI Team
Development | 2024-05-16 | 2024-07-31 | 96 | Not Started | 85,000 | Development Team
Testing & QA | 2024-08-01 | 2024-08-30 | 30 | Not Started | 15,000 | QA Engineers
Deployment & Go-Live | 2024-09-01 | 2024-09-15 | 15 | Planned | 8,000 | Operations Team
Post-Launch Review | 2024-09-16 | 2024-09-30 | 15 | Not Started | 3,000 | Project Manager
Total Estimated Cost: |  |  |  | $128,000